## Machine Issue List
Issue ID | Machine / Module | Issue Category | Issue/Enhancement Description | Customer Feedback | Impact / Risk | Priority | Remarks | Done
MT_001 | A300 Shell Assembly | PLC / Software | Machine Recipe Management | HMI required to have Recipe Page and User able to Create,Edit, and Delete Recipe. - Recipe for EBM, PC Green,PC Amber, PC Red, PC Clear - Include in Recipe :- * Robot point | 1. Shell have multiple Part number and Type, which lead to some variants that required specific recipe when production running. No ability to change recipe will impact on shell screwing result, Repeative teach point event and will impact production running. | High | 1. A real recipe page can’t be finished until the robot engineer decides how the robot will store and load a separate set of points for each recipe.
MT_002 | A300 Shell Assembly | PLC / Software | Robot Page to included in HMI page | HMI required to have Robot page for users to control, teach point, and reset Robot module. - Robot Page need to have button to Start, Stop, Reset robot, Speed Change, Run, Pause and Save - Robot Page need to shows current robot status, robot current axis value and robot current point ( such as Home or Standby point) - Robot page to have button selection for Move ( prepared a dropdown according to Robot program) that will let users to move robot to desired point when users attempt to do teach point. - Robot page need to let user perform teach point and the point need to be save in teach pendant. - Robot page to let user jog robot for all axis and user need to key in value for robot jog moving. Value must be in between 0.01mm to 10.00mm per jog. | 1. Robot only can be access through Teach Pendant and will need to open machine door bottom Panel door to access. 2. Automation team prefer to prohibited access to Teach Pendant due to possible misused and prevent programming or source code been access by others. 3. Current ways of teaching point using Teach Pendant might leads to wrong teach and will lead to longer down time. | High | 1
MT_003 | A300 Shell Assembly | PLC / Software | Shell CSV file | HMI/PLC to provide a log file for each of Shell process, Including : - Barcode - Torque Data - Result - Result remedy The data need to be log for every "New Lot" created and will be save on the HMI PC in Folder " Lot ID Number ". New Lot Id will create new folder. | 1. Current machine don't have specific data trace for shell that have been processed. 2. Current Data mixed up the overall data and difficult to segregate between each Shell that have been run. 3. These Data are importants for Automation team to monitor the machine performance and perform enhancement accordingly. | High | 1. For MT_003, the HMI now creates one CSV per shell, named <LotID>_<FoupID>_<Pass¦Fail>. The HMI reads the FOUP ID from Foup_Barcode (EM3050, String[20]), but nothing in the current PLC program writes to this address, so it is always empty. Questions. 1. Source of the FOUP ID: barcode scanner on the machine, operator scan/input, or CAMLINE? If there is a scanner, which device and interface is it? 2. Rework: for a rework shell, will the same FOUP ID be available again (e.g. re-scanned)? 3. Fail result: Overall_Fail (MR49601) is only set when CAMLINE is enabled. Can it be set for every shell that ends without Overall_Pass (step 360, or hard reset / removed shell)? Today the HMI assumes “no Pass = Fail”. 4. Lot ID: please confirm Lot_Info_DB_New_Lot_ID_Str (EM1501) stays valid from New Lot until End Lot. | 1. FOUP ID is empty because nothing in the PLC program ever writes EM3050. The HMI only reads it, to send to CAMLINE, and CAMLINE is bypassed on this machine. The HMI can’t fix this; it needs the PLC team, or a scanner. Until then, files are named …_NoFoupID_<time> 2. Lot ID empty causes by the old HMI code read it with length 0, so it always came back empty. That’s fixed now.
MT_004 | A300 Shell Assembly | PLC / Software | Lot ID and Recipe Management | Machine need to have Lot ID, Operator ID, Quantity and Recipe before able to run.Machine need to intialize after New Lot is created. Machine Init Done bit need to be off when user press "End Lot" Button. | 1. Lot ID will be use to trace back quantity of Shell process. 2. Lot ID will be use for communicating with camLine. | High
MT_005 | A300 Shell Assembly | PLC / Software | Add Initialize Button on HMI | HMI Main Page need to include Initialize Button for users to initialize the machine when anythings goes wrong. | 1. Current machine need users to press engineering button first before Initialize can be done by press Start Button. 2. This will leads to confusion for users and wrong step taken to initialize the machine. | High
MT_006 | A300 Shell Assembly | PLC / Software | Prompt Pop up Message when User attempt to Perform Hard Reset | Machine have a Hard reset function where users need to press reset for 10s before hard reset is activated. Shell also must be presence inside the machine and machine must be in running mode. Hard Reset should be able to perform at any conditions of the machine and a pop up should prompt for user to choose either Proceed or Cancel. Reduce the timer to 5s instead of 10s without machine need to be in certain state before able to initiated Hard Reset. | 1. Current conditions for Hard Reset is confusing and took some time to initiated. 2. Operator tends to take away the Shell when there is something wrong happen to the machine and not able to fullfil the conditions for hard reset. 3. No indicator are shown when Hard reset is initiated. | High
MT_007 | A300 Shell Assembly | PLC / Software | Robot Initialized Sequence | Robot initialized sequence will make robot to flush out screw. After monitoring, robot tends to flush out screw at any places instead of flushing at desinated place. | 1. Robot to flush the screw on Shell and will lead to cosmetics issues. 2. Robot should move to standby/home point before flushing the screw. | High
MT_008 | A300 Shell Assembly | PLC / Software | Remove Top Clamp Sequence | Current machine having Top Clamp where cylinders are uses to clamp the Shell for alignment purpose. After monitoring, We decide to exclude the Top Clamp Sequence as we believe Top Clamp don’t contribute to Shell Alignments and working well without it. | 1. Reduce cycle time and improve machine performance. | Medium
MT_009 | A300 Shell Assembly | PLC / Software | Error Message to prompt Spare Error | Some error message not prompt the actual message and lead to confusions | 1. All Errors and Warnings mapped to the machine must prompt correctly on HMI to prevent longer down time for troubleshootings. | Medium
MT_010 | A300 Shell Assembly | PLC / Software | Machine required multiple time to access Left/Right start button before machine run | Machine sometime need users to trigger machine to start running. Operator tends to confuse when same action need to be done twice even instructions have been followed from HMI. | 1. User need to press start mutiple time eventhough instruction on HMI have been fullfil. | Medium

## Lists (hidden)
Priority | Status | Confirmation | Category
Low | Open | Pending | Electrical
Medium | In Progress | Accepted | Mechanical
High | Monitoring | Rejected | PLC / Software
Critical | Waiting for Customer | Further Action Required | HMI
| Waiting for Vendor |  | Sensor / Instrument
| Closed |  | Pneumatic
| On Hold |  | Safety
Quality
Cycle Time
Other